## Sheet1
17019105 | C++ Particle System Library
Week Date Start | Tasks set for this week | Outcomes achieved | Questions/tasks to be taken forward
2019-10-15 | Get a triangle rendered using Vulkan. | Managed to get vulkan include in the project and the validation layers implemented Get the triangle rendered. | Get the triangle rendered.
2019-10-22 | Get a cube rendered using Vulkan. | Managed to get a triangle rendered. | Get the cube rendered.
2019-10-29 | Get a cube rendered using Vulkan. | No progress with the practical side of the project but have managed to research some more about vulkan and command buffers. | Get the cube rendered.
2019-11-05 | Get a cube rendered using Vulkan. | Had the data for the cube in the project but didn’t managed to get it rendered as the depth stencil buffer wasn’t correctly setup so it still wasn’t in 3D. | Get the cube rendered.
2019-11-12 | Get a cube rendered using Vulkan. | Managed to get a cube rendered as well as model loading so any .obj files could be loaded.
2019-11-19 | Get multiple rendered using Vulkan. | Managed to get multiple cubes as well as instancing working so any number of cubes can be generated. | Research more about the shaders and the descriptor sets/pipelines as they are nessecary for having multiple objects of different types.
2019-11-26 | Extract out the nessary code for the library so the foundations for it can start being implemented. | Extracted out some of the code such as the functions that create the logical and physical devices but need to reorganise the VkPipeline as to allow for creating pipeline for differnet objects. | Research more on the lighting grid hierarchy in preparation for the start of its implementation
2019-12-03 | Get the code base in place where it is starting to look like a scene with only the nessary code in it. | Still trying to extract the necessary bits of code for the library but not going well. | Switch to making the particle system act like a particle system and not just cubes moving in one direction.
2020-01-06 | Have the prototype ready to demonstrate the progress that was made with the physics for the particle system and the lighting. | Managed to implement a basic flow field, so the instanced particles are floating around and seeming to have more natural or fluid movements. | Implement lighting for the prototype.
2020-01-12 | Imlpement lighting for the prototype and be ready for the demo on the 15th. | Very basic lighting effects was achieved by changing the colour of the vertices of the sphere to a value between black and orange to simulate the effect of the object being light up. | Clear up code so it is more manageable going forward with the project.
2020-01-19 | Clean up code so it is usable/manageable as well as getting multiple models working (not instancing). | Managed to get multiple models displaying, with some of the code base cleared up by taking the buffer, texture, shader, descriptor set creation and management out of main.cpp. | Further clean up the code base.
2020-01-26 | Clean up code base more. | Got dynamic loading of objects (it will be different based on the parameters) and started looking into point sprites. | Get point sprites working for the particle system.
2020-02-02 | Implement point sprites for the particle system. | Manged to get point sprites working, so was able to render over 100,000 particles. | Get alpha blending working so a simple fuzzy texture can be used to give a more realistic look to the particles. Get a profiler working for the program to see where the bottle necking is occurring in the project.
2020-02-09 | Implement alpha blending as well as get a profiler to find the bottle neck. | Implemented alpha blending so the particles now look like particles instead of square texture with tomatoes on it. | Look into signed distance fields for making the particles attracted to an .obj file loaded and then follow the surface of the object.